## H2gether Test Case (hidden)
H2gether Test Cases |  |  |  | Android Application Name: | H2gether
|  |  |  | Members: | Jelisha Ruth B. Bugnon, Irish Micole T. Cando
Ma. Jensen Nicole C. Dela Rosa, John Ric C. Merque
Feature | STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
Log-in/Sign-up | 1.1 | User fills log-in credentials and clicks proceed button | 2023-07-01 | The user will be directed to the start up section
| 1.2 | User fills incorrect log-in credentials and clicks proceed button | 2023-07-01 | The app will prompt a log-in error and ask again for log-in credentials
| 1.3 | New user swipes up to create an account | 2023-07-01 | The user will be directed to the sign up section
| 1.4 | User fills credentials and clicks sign-up | 2023-07-01 | App makes new account for the user
| 1.5 | User logs-in using gmail, facebook | 2023-07-01 | App links existing accounts
Start-up Section | 2.1 | User clicks the screen | 2023-07-01 | Start-up pages turns to the next page
| 2.2 | User clicks the skip button | 2023-07-01 | Start-up pages are skipped and user will be directed to personalization page
User Confguraration and Personalzaton | 3.1 | User selects sex, weight, height, activity level, and sleep schedule | 2023-07-02 | App saves informaton to account database
| 3.2 | User clicks next button | 2023-07-02 | User will be directed to next configuration page
| 3.3 | User fills the last configuraton and clicks next | 2023-07-02 | App creates water plan
Homepage | 4.1 | User clicks drink button on the homepage | 2023-07-02 | App asks for input regarding water intake (mL)
| 4.2 | User fills input and clicks drink button | 2023-07-02 | App saves informaton and updates statstic graphics and percentage
| 4.3 | User clicks, water, rank, family, and me buttons | 2023-07-02 | User will be directed to corresponding sections
Profile | 5.1 | User clicks Reminders Button | 2023-07-03 | User wll be directed to reminders section
| 5.2 | User clicks adds reminder icon | 2023-07-03 | App wll ask user for reminder schedule
| 5.3 | User inputs reminder schedule | 2023-07-03 | App saves the reminder and notifies user upon due.
| 5.4 | User enables pre-existing remind buttons | 2023-07-03 | App sets the reminder
| 5.5 | User clicks Hydration Tips | 2023-07-03 | User will be directed to Hydraton tips sections
| 5.6 | User clicks screen in the hydration tips | 2023-07-03 | User will be directed to next tip
Community Ranking | 6.1 | User clicks family ranking | 2023-07-03 | App displays family ranking, stars and water intake
| 6.2 | User clicks friends ranking | 2023-07-03 | App displays friends ranking, stars and water intake
Family Tracking | 6.3 | User views family members | 2023-07-04 | App displays famly members
| 6.4 | User clicks Reminders Button | 2023-07-04 | App prompts confirmation and sends reminder
| 6.5 | User clicks add Family member | 2023-07-04 | App adds selected account as user's family member
Settings | 7.1 | User clicks change language button | 2023-07-04 | App prompts available language selection
| 7.2 | User selects language | 2023-07-04 | App integrates selected language
| 7.3 | User clicks Rate us buton | 2023-07-04 | Promps star rating and integrates rating to GooglePlay
| 7.4 | User clicks send feedback button | 2023-07-04 | Proceeds to message prompts to admin email
| 7.5 | User clicks Privacy Policy | 2023-07-04 | App displays Privacy policy

## Unit Testing
H2gether - Unit Testing |  |  |  | Android Application Name: | H2gether
|  |  |  | Members: | Jelisha Ruth B. Bugnon, Irish Micole T. Cando
Ma. Jensen Nicole C. Dela Rosa, John Ric C. Merque
Feature | STEP ID | STEP DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | REVALIDATION: PASS/FAIL | NOTES
Sign-up | 1.1 | User enters a valid email field respectively. Email should follow the standard format (@gmail.com) | 2023-06-11 | The system will accept the email without displaying any error messages. | The app accepted valid email without displaying any error message. | PASSED
| 1.1.1 | User enters an invalid email address(missing @ symbol) in the email field. | 2023-06-11 | The system will detect the invalid email address and display an error message indicating that the email address is invalid. | The app detected an invalid email address and displayed "Invalid Email." | PASSED
The user will not be able to proceed with the sign-up process until a valid email address is entered.
| 1.2 | The user enters a strong and valid password in the password field and ensure that the confirm password field is filled correctly. | 2023-06-11 | The system will accept the password without displaying any error messages. | The app accepted the password without displaying any error messages. | PASSED
| 1.2.1 | User enters an invalid password in the password field. The password should not meet the requirements set by the application. | 2023-06-11 | The system will detect the invalid password and display an error message indicating that the password is invalid or doesn't meet the password requirements. | The app identified an invalid password, but unfortunately, the error message cannot be fully read due to the way it is currently displayed. |  | Can we use multiple lines in error message? Or let's make the error message more concise like this: “Password must be at least 8 characters long and include 1 letter and 1 number.” | PASSED | TEST DATE: 06 20 2023 The app correctly identifies an invalid password, and fortunately, the error message is displayed in its entirety, allowing the user to read and understand the reason for the password's invalidity.
The user will not be able to proceed with the sign-up process until a valid and strong password is entered.
The error message will clearly guide the user on how to correct the issue (suggesting choosing a longer password or adding complexity such as uppercase letters, numbers, or special characters).
| 1.2.2 | User enters a different password or an invalid value in the confirm password field. | 2023-06-11 | The system will display an error message indicating the mismatch. | The app displayed an error indicating the mismatch. | PASSED
| 1.3 | User clicks the toggle icon in password fields. | 2023-06-11 | The system will hide/unhide the password upon clicking | The toggle icon functions properly. | PASSED
| 1.4 | User clicks on the "Sign Up" button to initiate the sign-up process. | 2023-06-11 | The user will now have an account and be able to access the application's features and functionality. The user should be directed to preface pages. | Account created, the user is directed to preface pages. | PASSED
| 1.5 | User clicks "Sign In" | 2023-06-11 | The user will be directed to the sign in page. | The user is directed to the sign in page. | PASSED
Log-in | 2.1 | User enters valid email in email field. | 2023-06-12 | The system will accept the entered email without displaying any error messages | The app accepted the entered email without displaying any error message. | PASSED
| 2.2 | User enters password. | 2023-06-12 | The system will validate the password without any errors. | The app validates the password without displaying any error. | PASSED
| 2.3 | User clicks "Sign In" button | 2023-06-12 | The user will be successfully logged in and granted access to the application's features and functionality. | Log in successful. | PASSED
| 2.4 | User enters an invalid email and clicks the sign-in button. | 2023-06-12 | Upon clicking the sign-in button, the user will be presented with an error message indicating that the email or username is incorrect or not recognized. | The app displayed an error: "com.google.firebase.auth.FirebaseAuthInvalidCredentialsException: The email… |  | The app should display that the entered email is invalid. | PASSED | TEST DATE: 06 20 2023 The app displayed a customized error message: "Invalid email address"
| 2.4.1 | User enters a password that is incorrect or doesn't match the provided email or username. | 2023-06-12 | The user will be presented with an error message indicating that the password is incorrect. | The app displayed an error: "com.google.firebase.auth.FirebaseAuthInvalidCredentialsException: There is no use.. |  | The app should display that the password is incorrect. | PASSED | TEST DATE: 06 20 2023 The app displayed a customized error message that entered password is incorrect.
| 2.5 | User clicks the toggle icon in password field. | 2023-06-12 | The system will hide/unhide the password upon clicking. | The toggle icon functions properly. | PASSED
| 2.6 | User clicks remember me. | 2023-06-20 | The system will provide the login credentials of user in log-in page. | The system provided the login credentials of user in log-in page. | PASSED
| 2.7 | User clicks forgot password |  | The user will be redirected to forgot password page.
| 2.8 | User clicks sign-in with Google. |  | In sign-up with Google, the user will be redirected to a Google login page or presented with a Google authorization pop-up.
The user should be successfully logged in.
| 2.9 | User clicks "Register" |  | The user will be directed to the sign-up page. | The user is directed to the sign up page. | PASSED
Preface | 3.1 | User clicks the the next button | 2023-06-12 | Start-up pages turns to the next page. | The Next button functions as expected and performs its intended functionality without any issues. | PASSED
| 3.2 | User clicks the back button | 2023-06-12 | By clicking the back button, the next page in the sequence will be displayed. | The Back button functions as expected and performs its intended functionality without any issues. | PASSED
| 3.3 | User clicks the skip button | 2023-06-12 | Start-up pages are skipped and user will be directed to configuration and personalization page. | Skip button direct the user to personalization page. | PASSED
| 3.4 | User clicks get started button. | 2023-06-12 | The user will be directed to the configuration and personalization pages. | Get started button direct the user to the configuration and personalization page. | PASSED
User Configuration and Personalization | 4.1 | User attempts to scroll up and down on the selection list for gender, weight, height, activity level and sleep schedule. | 2023-06-13 | The list will be move upward/backward smoothly, allowing the user to view additional choices that were initially hidden. | The list moves smoothly upward and backward, allowing the user to view all available options. | PASSED
| 4.2 | User selects their sex, weight, height, activity level, and sleep schedule | 2023-06-13 | The app saves informaton to account database. | All user selections are clickable. The user configuration data reflects on the database in real time. | PASSED
| 4.3 | User clicks the next button. | 2023-06-13 | The user will be directed to next configuration page. | Next buttons are working properly. | PASSED
| 4.4 | User fills the last configuraton and clicks next. |  | The app creates water plan.
Homepage | 5.1 | User clicks drink button or the plus sign on the homepage | 07/19/2023 | The app asks for input regarding water intake (mL) | The app displays a "Please select an option" message after clicking. | PASSED
| 5.2 | User fills input and clicks drink button. | 07/19/2024 | App saves informaton and updates statstic graphics and percentage | After clicking a drink option or amount of water intake, it adds up to the progress bar | PASSED
| 5.2.1 | User fills input greater than their daily water intake. | 07/19/2025 | The system will detect the invalid input and display an error message indicating that it exceeds their recommended daily water intake. | The app accepts the value greater than the recommended intake and displays a 100% on the progress bar and does not allow additional input of water intake. | PASSED | "Target water already achieved" message is displayed
| 5.2.2 | User fills input negative values | 07/19/2026 | The system will detect the invalid input and display an error message indicating that input should not be negative. | The app accepts the negative value for water intake but displays a negative percentage on the progress bar. | PASSED
| 5.2.3 | User fills input with letters or special character. | 07/19/2027 | The system will detect the invalid input and display an error message indicating that letters and special character is not accepted. | The app only displays a numerical keyboard and won't allow letters or other special characters.
| 5.2.4 | User clicks the "x" or close button | 07/19/2028 | The input box for adding water intake will be closed. | After clicking the cancel button, it closes the input box for the water intake. | PASSED
| 5.3 | User clicks navigation buttons (home, ranking, family, and profile). | 07/19/2029 | The user will be redirected to the intended pages. | The app redirected the user to the pages of the clicked buttons. | PASSED
Community Ranking | 6.1 | User clicks family ranking. |  | The app display will display family ranking, stars and water intake.
| 6.2 | User clicks friends ranking |  | The app displays friends anking, stars and water intake.
| 6.3 | User clicks back button. |  | The user will be directed to the previous page or screen that was visited before.
Family Tracking | 7.1 | User views family members |  | The app will display family members
| 7.2 | User clicks Reminders Button |  | The app will prompt confirmation and sends reminder.
The app will show a success message indicating that the reminder has been sent.
| 7.2.1 | User clicks cancel button |  | The prompt will be closed.
| 7.3 | User clicks add Family member |  | The app will add selected account as user's family member.
| 7.4 | User clicks back button. |  | The user will be directed to the previous page or screen that was visited before.
Profile | 8.1 | User clicks Me Button on the Navigation Bar. | 07/19/2023 | The user will be redirected to the user's profile page. | The app redirected the user to the user's profile page and displayed the user data such as gender, age, weight, height, and activity level. | PASSED
| 8.1.1 | User clicks Edit Button. | 07/19/2023 | The app will display the user experience personalization to cater changes in user's information and activity level. | The app will redirect the user to experience personalization in case of changes in their information and activity level. | PASSED
| 8.1.2 | User clicks Log out button. | 07/19/2023 | The app will log out the user's account. | The app redirected the user back to the log-in page and logged out the existing account. | PASSED
Settings | 9.1 | User clicks change language button |  | The app will prompt available language selection
| 9.2 | User selects language |  | The app integrates selected language
| 9.3 | User clicks Rate us buton |  | The app will prompt star rating and integrates rating to GooglePlay
| 9.4 | User clicks send feedback button |  | The app will proceeds to message prompts to admin email
| 9.5 | User clicks Privacy Policy |  | The app will display Privacy policy
Splash Screen | 10 | Opens the app | 2023-06-24 | The app will display the app logo and app name and directs to the Sign In Page | The app displays the app logo and app name and directs the user to the Sign In Page | PASSED
Creating a Plan | 11 | Clicks the next button in the activity level configuration page | 2023-06-24 | Displays the progress animation and directs the user to the Home page | The app displays the creating plan animation after clicking the next button in the last configuration page and also directs the user to the home page | PASSED
Hydration Tips Page | 12.1 | User clicks the Tips icon in navigation bar. | 2023-07-12 | The app will display Hydration Tips page. | The app displays the Hydration Tips page. | PASSED
| 12.2 | User swipes the screen to the right or left. | 2023-07-12 | By swiping left on the screen, the next page in the sequence will be displayed. | The app displays the next page of Hydration Tips. | PASSED
| 12.3 |  |  | By swiping right on the screen, the previous page in the sequence will be displayed. | The app displays the previous page of Hydration Tips. | PASSED
Weather Page | 13 | User swipes down the page. | 2023-07-22 | By swiping down the page, the latest weather data will be fetched and displayed. | The app displays the latest weather data after refreshing the page. | PASSED | The weather data updates after an hour.
Statistics Page | 14 | Clicks the statistics button on the navigation bar. | 2023-07-22 | By clicking the statistics button on the navigation bar, the app will direct the user to the statistics page and display the weekly water consumption. | When the statistics button is clicked, the user is directed to the statistics page, which displays the user's water consumption for the week. | PASSED

## User Acceptance Testing (UAT)
H2gether - User Acceptance Testing | [5 empty] | Android Application Name: | H2gether
[6 empty] | Members: | Jelisha Ruth B. Bugnon, Irish Micole T. Cando
Ma. Jensen Nicole C. Dela Rosa, John Ric C. Merque
Feature | TEST CASE | TEST CASE ID | TEST STEPS | DESCRIPTION | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | REVALIDATION: PASS/FAIL | NOTES
Sign-Up | Successful sign-up | TC-001 | Sign-up by filling in valid email and password. | Verify that a user can successfully sign up with valid information. | 2023-06-11 | The user should be successfully registered and directed to preface pages. | Account successfully created and user is directed to preface pages. | PASSED
| Error handling | TC-002 | Leave one or more required fields empty (name, email, password) and observe the alert messages that will show. | Verify that appropriate error handling is in place for various scenarios during the sign-up process. | 2023-06-11 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displayed "Empty fields are not allowed." and "Email is invalid." in step 1 and step 2 respectively. | PASSED
|  |  | Add invalid email and observe the alert messages that will show. |  |  |  |  | PASSED
| Password Requirements | TC-003 | Enter a password that should not meet the system requirements. | Verify that the system enforces password strength requirements during sign-up. | 2023-06-11 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password, but unfortunately, the error message cannot be fully read due to the way it is currently displayed. |  | Make the error message more concise like this: “Password must be at least 8 characters long and include 1 letter and 1 number.” | PASSED | TEST DATE: 06 20 2023 The app accurately displays the full error message for an invalid password, enabling users to understand why the password is invalid.
| Password and Confirm Password Mismatch | TC-004 | Enter different password in confirm password field. | Verify that an error message is displayed when the password and confirm password fields do not match during registration. | 2023-06-11 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED
| Existing user validation | TC-005 | Enter an email address that is already registered in the system. | Verifies that the system detects and rejects sign-up attempts with an email address already registered. | 2023-06-11 | An error message should be shown, indicating that the email address is already registered. | The app displayed the default message: "com.google.firebase.auth.FirebaseAuthUserCollisionException:.." which may confuse the user as it presents technical information that may not be easily understandable to them. |  | Display a customized error message like this: "An account with this email already exists." | PASSED | TEST DATE: 06 20 2023 The app displayed a customized error message "An account already exists."
Log-In | Valid Log-in | TC-007 | Log-in by filling in valid email and password. | Verify that users can log in successfully with valid credentials | 2023-06-12 | The user should be directed to the home page after successfully logging in. | Login with valid email and password is successful. However, the integration of Google login is still in progress and has not been completed yet.
Log-in with Google
| Invalid Log-in | TC-008 | Enter an invalid email | Verify that appropriate error messages are displayed for invalid login attempts. | 2023-06-12 | Consistently displays the error message for invalid credentials. | The app displayed technical error message which may confuse users. |  | The app should display appropriate error messages to notify the user about the issues. For example: If the entered email is invalid: "Invalid email. Please enter a valid email address." If the entered password is incorrect: "Incorrect password. Please enter the correct password." | PASSED | TEST DATE: 06 20 2023 The app displayed a customized error messages for invalid log-in scenarios.
Enter an incorrect password
| Nonexisting Account Validation | TC-009 | Enter an email address that does not exist in the system | Verify that the app displays an error message indicating that the account does not exist. | 2023-06-12 | Consistently displays the error message for nonexisiting accounts. | The app displayed technical error message which may confuse users. |  | The app should display appropriate error message. For example: "Account not found. Please check the email entered or create a new account." | PASSED | TEST DATE: 06 20 2023 The app displayed a customized error messages for nonexisting user account.
Enter a valid or invalid password
Preface | Sequential navigation through preface pages and Get started button | TC-011 | Tap on the next button. | Verify that users can navigate through the preface pages in a sequential order by using next button and that "get started" button on the last preface page functions properly. | 2023-06-12 | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | Each preface page is displayed in the correct order, ensuring the sequential progression of content. The next button smoothly transitions to the next preface page without encountering any errors. Clicking the "get started" button successfully directs the user to the configuration and personalization pages, indicating a smooth transition to the subsequent stages of the application flow. | PASSED
Tap on the "Get started" buton.
| Backward navigation through preface pages | TC-012 | Tap on the back button to go back to the previous pages. | Verify that users can navigate backward through the preface pages. | 2023-06-12 | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | Each preface page is displayed in the correct order when navigating backward, ensuring the sequential progression of content is maintained. The back button seamlessly transitions to the previous preface page without encountering any errors, allowing users to navigate back through the preface pages as expected. | PASSED
| Skip preface pages | TC-013 | Tap on the "skip" button on the top-right corner of the screen. | Verify that the skip option works. | 2023-06-12 | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | Upon clicking "skip," the user is successfully redirected to the configuration and personalization pages, bypassing the remaining preface pages. | PASSED
User Configuraration and Personalization | Valid User Selection | TC-014 | Select user sex | Verify that the app accepts the input values and updates the user's profile accordingly. | 2023-06-13 | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | After selecting valid user input, the user is directed to the next configuration page. | PASSED
Select user age
Select user weight
Select user height
Select activity level
| Invalid User Selection | TC-015 | Select nothing from the sex and activity level selections. | Verify that the "next" button should not function. | 2023-06-13 | Would not proceed to the next configuration page. | The next button is not clickable. | PASSED
Homepage | Add water intake | TC-016 | Enter a valid quantity of water intake in mL. | Verify that the app successfully adds the water intake and updates the progress towards the daily target. | 07/19/2023 | The user interface should reflect the updated water intake appropriately. | The app accepts the input value for the water intake and displays it on the progress bar and constantly updates it with every input. | PASSED
| Invalid water intake | TC-017 | Enter an invalid quanitity (negative value, zero, or non-numeric input) | Verify that the app displays an appropriate error message indicating the invalid input. | 07/19/2023 | An error message should be displayed, informing the user about the invalid input. | The "Please select an option" message keeps on displaying on the app. | PASSED
| Exceeding daily water intake target | TC-018 | Enter a water intake value greater than the daily recommended target. | Verify that the app prevents adding water intake exceeding the daily target and displays an appropriate error message. | 07/19/2023 | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | The app accepts the excessive input value and displays a 100% on the progress bar and does not accept any more input after that and displays a "Target water already achieved" message. | PASSED
| Missing Water Intake Entry | TC-019 | Clicking "add" without input | Verify that the app displays an appropriate error message indicating the missing input |  | An error message should be displayed, informing the user that input is required. | A "Please select an option" message is displayed, requesting the user to select an amount of water intake on the displayed options. | PASSED
| Navigation Bars | TC-020 | Tap on each navigation bar. | Verify that the app navigates to the corresponding page accurately. |  | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | The app takes the user to the intended page and displays the content of that page selected. | PASSED
Community Ranking | View Community Ranking | TC-021 | Click family ranking | Verify that the user's ranking is visible and accurately displayed in friends and family ranking. Additionally, it ensures that the ranking order is based on the accomplishment of their recommended daily water intake. |  | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher.
Click friends ranking
Family Tracking | Sending reminder to a family member | TC-022 | Click the the button to send a reminder to a family member. | Verify that the user can send a reminder to a family member. |  | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent.
Access the receiver account and confirm if the reminder is visible.
| Add a family member. | TC-023 | Click on the add member to the list. | Verify that the user can add new family member to the family tracking list. |  | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list.
Enter the required information.
Check if the account is already added to the family tracking list.
Profile | Profile Actions | TC-025 | Click the settings button. | Verify that all buttons consistently respond to user clicks and perform the intended actions, such as switching pages. | 07/19/2023 | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | After clicking the settings button, the app redirects the user to the settings page that allows them to either submit a feedback or read the privacy policy and about us. On the hydration tips tab, it allows the user to view the tips by swiping left or right to navigate through the page. | PASSED
Click the hydration tips tab.
| Edit User Configuration and Personalization with Valid Value | TC-026 | Replace the user input values with valid ones. | Verify that the app updates the user information, creates a new plan, and reflects the changes throughout the app. | 07/19/2023 | Update the user information, create a new plan, and reflect the changes throughout the app. | The app updates the user information, and activity level, creating a new plan based on the changes made in the user personalization and configuration. | PASSED
| Edit User Configuration and Personalization with Invalid Value | TC-027 | Replace the user input values with invalid ones. | Verify that the app will display an error message and therefore not create a new plan. | 07/19/2023 | Consistently displays an error message for invalid input values. | The app does not allow the user to continue after invalid input or no input at all. | PASSED
Settings | App Rating | TC-029 | Click the Rate us tab. | Verify that the app redirects the user to the playstore. |  | The app redirects the user to the playstore.
|  |  | Enter the rating and/or app review. | Verify that the playstore displays the submitted rating and review accurately. |  | The playstore displays the submitted rating and review accurately.
| Feedback | TC-030 | Click the Feedback tab. | Verify that the app will display the feedback submission form. |  | The feedback submission form displays.
|  |  | Enter feedback. | Verify that the app acknowledges the user's feedback and displays a confirmation message. |  | The app receives the feedback and stores it in the database.
| Privacy Policy | TC-031 | Click the Privacy policy tab. | Verify that the app consistently provides access to the privacy policy. |  | The app display the privacy policy page.
Splash Screen | Splash Screen | TC-032 | Opens the app | Verify that the app displays the logo and name and directs to the Sign In Page | 2023-06-24 | The app will display the app logo and app name and directs to the Sign In Page | The app displays the app logo and app name and directs the user to the Sign In Page | PASSED
Creating a Plan | Creating a Plan | TC-033 | Finish answering the user configuration page | Verify that the app will display the loading animation and direct the user to the Home Page | 2023-06-24 | Displays the progress animation and directs the user to the Home page | The app displays the creating plan animation after finishing the configuration page and also directs the user to the home page | PASSED
Hydration Pages | Sequential navigation through Hydration Tips pages | TC-034 | Swipes the screen to the right or left | Verify that users can navigate through the hydration tips pages in a sequential order by swiping left and right. | 2023-07-12 | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | The hydration tips pages appear in the correct sequence and have smooth and responsive navigation between the pages when swiping, without any delays. | PASSED
Weather Page | Updated display of data weather | TC-035 | User swipes down the page. | Verify that the refresh function works. | 2023-07-19 | By swiping down the page, the latest weather data will be fetched and displayed. | The weather page refreshes after swiping down the page and updates to the latest weather data that changes real-time after an hour. | PASSED
Statistics Page | Real-time display of weekly water consumption | TC-036 | Clicks the statistics button on the navigation bar. | Verify that the statistics page will display real-time data of the user | 2023-07-22 | By clicking the statistics button, the weekly water consumption of the user will be displayed through line graph. | When the statistics button is clicked, the user's water consumption for the week is displayed as a line graph. | PASSED

## Regression Testing
H2gether - Regression Testing | [6 empty] | Android Application Name: | H2gether
[7 empty] | Members: | Jelisha Ruth B. Bugnon, Irish Micole T. Cando
Ma. Jensen Nicole C. Dela Rosa, John Ric C. Merque
Feature | TEST CASE | TEST CASE ID | TEST STEPS | DESCRIPTION | VERSION 1 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 2 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 3 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 4 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 5 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 6 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 7 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 8 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES | VERSION 9 | TEST DATE | EXPECTED RESULTS | ACTUAL RESULTS | PASS / FAIL | ADDITIONAL NOTES
Sign-Up | Successful sign-up | TC-001 | Sign-up by filling in valid email and password. | Verify that a user can successfully sign up with valid information. |  | 2023-06-11 | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | Account successfully created and user is directed to preface pages. | PASSED |  |  | 2023-06-13 | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | Account successfully created and user is directed to preface pages. | PASSED |  |  | 2023-06-13 | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | Account successfully created and user is directed to preface pages | PASSED |  |  | 2023-06-13 | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | Account successfully created and user is directed to preface pages | PASSED |  |  | 2023-06-24 | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | Account successfully created and user is directed to preface pages | PASSED |  |  | 2023-07-12 | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | The app only prompts "Choose a Google account" but does not create a new account in Firebase. The user is also not redirected to the preface pages. | FAILED |  |  | 07/19/2023 | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | The app only prompts "Choose a Google account" but does not create a new account in Firebase. The user is also not redirected to the preface pages. | FAILED |  |  |  | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google. | [5 empty] | The user should be successfully registered and directed to preface pages. If the user wants to sign-up with Google, the user will be redirected to log in page of Google.
Sign-in with Google
| Error handling | TC-002 | Leave one or more required fields empty (name, email, password) and observe the alert messages that will show. | Verify that appropriate error handling is in place for various scenarios during the sign-up process. |  | 2023-06-11 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displayed "Empty fields are not allowed." and "Email is invalid." in step 1 and step 2 respectively. | PASSED |  |  | 2023-06-13 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displayed "Empty fields are not allowed." and "Email is invalid." in step 1 and step 2 respectively. | PASSED |  |  | 2023-06-13 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displayed "Empty fields are not allowed." and "Email is invalid." in step 1 and step 2 respectively. | PASSED |  |  | 2023-06-13 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displayed "Empty fields are not allowed." However, it accepted an email with an extension of @ggmail.com, which is supposedly an invalid email. | FAILED |  |  | 2023-06-24 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displays an alert message "Please enter email or password." | PASSED |  |  | 2023-07-12 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displays an alert message "Please enter email or password." | PASSED |  |  | 07/19/2023 | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | The app displays an alert message "Please enter email or password." | PASSED |  |  |  | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid. | [5 empty] | In step 1, an alert message should be displayed indicating that empty fields are not allowed. In step 2, an alert message should be displayed indicating that email is invalid.
|  |  | Add invalid email and observe the alert messages that will show. | [5 empty] | PASSED | [22 empty] | The app still accepts an email with an extension of @ggmail.com, which is supposedly an invalid email. | FAILED |  |  |  |  | The app still accepts an email with an extension of @ggmail.com, which is supposedly an invalid email. | PASSED |  |  |  |  | The app still accepts an email with an extension of @ggmail.com, which is supposedly an invalid email. | PASSED
| Password Requirements | TC-003 | Enter a password that should not meet the system requirements. | Verify that the system enforces password strength requirements during sign-up. |  | 2023-06-11 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password, but unfortunately, the error message cannot be fully read due to the way it is currently displayed. | FAILED | Make the error message more concise like this: “Password must be at least 8 characters long and include 1 letter and 1 number.” |  | 2023-06-13 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password and displayed appropriate error message: "Password must be at least 8 characters long and include 1 letter and 1 number.” | PASSED |  |  | 2023-06-13 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password and displayed appropriate error message: "Password must be at least 8 characters long and include 1 letter and 1 number.” | PASSED |  |  | 2023-06-13 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password and displayed an appropriate error message: "Password must be at least 8 characters long and include 1 letter and 1 number." However, it still doesn't accept passwords with different characters despite meeting the requirement (ex: @$%^&nnd123). | FAILED | Revise the displayed error message and indicate that the password should only be numbers and letters and not other special characters. |  | 2023-06-24 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password and displayed an appropriate error message: "Password must be at least 8 characters long and include 1 letter and 1 number." However, it still doesn't accept passwords with different characters despite meeting the requirement (ex: @$%^&nnd123). | FAILED | Revise the displayed error message and indicate that the password should only be numbers and letters and not other special characters. |  | 2023-07-12 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password and displayed an appropriate error message: "Password must be at least 8 characters long and include 1 letter and 1 number." However, it still doesn't accept passwords with different characters despite meeting the requirement (ex: @$%^&nnd123). | FAILED | Revise the displayed error message and indicate that the password should only be numbers and letters and not other special characters. |  | 07/19/2023 | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | The app identified an invalid password and displayed an appropriate error message: "Password must be at least 8 characters long and include 1 letter and 1 number." However, it still doesn't accept passwords with different characters despite meeting the requirement (ex: @$%^&nnd123). | FAILED |  |  |  | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided. | [5 empty] | An error message should be shown, indicating that the password does not meet the strength requirements and the sign-up attempt should not proceed until a strong password is provided.
| Password and Confirm Password Mismatch | TC-004 | Enter different password in confirm password field. | Verify that an error message is displayed when the password and confirm password fields do not match during registration. |  | 2023-06-11 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED |  |  | 2023-06-13 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED |  |  | 2023-06-13 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED |  |  | 2023-06-13 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED |  |  | 2023-06-24 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED |  |  | 2023-07-12 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED |  |  | 07/19/2023 | An error message should be displayed indicating that the passwords do not match. | The app displayed an error indicating the mismatch. | PASSED |  |  |  | An error message should be displayed indicating that the passwords do not match. | [5 empty] | An error message should be displayed indicating that the passwords do not match.
| Existing user validation | TC-005 | Enter an email address that is already registered in the system. | Verifies that the system detects and rejects sign-up attempts with an email address already registered. |  | 2023-06-11 | An error message should be shown, indicating that the email address is already registered. | The app displayed the default message: "com.google.firebase.auth.FirebaseAuthUserCollisionException:.." which may confuse the user as it presents technical information that may not be easily understandable to them. | FAILED | Display a customized error message like this: "An account with this email already exists." |  | 2023-06-13 | An error message should be shown, indicating that the email address is already registered. | The app displayed the default message: "com.google.firebase.auth.FirebaseAuthUserCollisionException:.." which may confuse the user as it presents technical information that may not be easily understandable to them. | FAILED | Same result with Version 1. Display a customized error message like this: "An account with this email already exists." |  | 2023-06-13 | An error message should be shown, indicating that the email address is already registered. | The app displayed the default message: "com.google.firebase.auth.FirebaseAuthUserCollisionException:.." which may confuse the user as it presents technical information that may not be easily understandable to them. | FAILED | Still the same result in version 1 and 2. Display a customized error message like this: "An account with this email already exists." |  | 2023-06-13 | An error message should be shown, indicating that the email address is already registered. | The app displayed the default message: "com.google.firebase.auth.FirebaseAuthUserCollisionException:.." which may confuse the user as it presents technical information that may not be easily understandable to them. | FAILED | Display a customized error message like this: "An account with this email already exists." |  | 2023-06-24 | An error message should be shown, indicating that the email address is already registered. | The app displayed an alert message saying "An account with this email already exists" | PASSED |  |  | 2023-07-12 | An error message should be shown, indicating that the email address is already registered. | The app displayed an alert message saying "An account with this email already exists" | PASSED |  |  | 07/19/2023 | An error message should be shown, indicating that the email address is already registered. | The app displayed an alert message saying "An account with this email already exists" | PASSED |  |  |  | An error message should be shown, indicating that the email address is already registered. | [5 empty] | An error message should be shown, indicating that the email address is already registered.
Log-In | Valid Log-in | TC-007 | Log-in by filling in valid email and password. | Verify that users can log in successfully with valid credentials |  |  | The user should be directed to the home page after successfully logging in. |  |  |  |  | 2023-06-13 | The user should be directed to the home page after successfully logging in. | Login with valid email and password is successful. However, the integration of Google login is still in progress and has not been completed yet. | FAILED |  |  | 2023-06-13 | The user should be directed to the home page after successfully logging in. | Login with valid email and password is successful. However, the integration of Google login is still in progress and has not been completed yet. | FAILED |  |  | 2023-06-13 | The user should be directed to the home page after successfully logging in. | Logging in with a valid email and password was successful. However, the integration of Google Login is still in progress and has not been completed yet. Additionally, after successfully logging in, the user is still directed to the user configuration page. Upon trying to select user sex again and clicking the next button, it displayed an error message "Please set sex" despite selecting one; hence, it doesn't proceed to the next configuration page. | FAILED |  |  | 2023-06-24 | The user should be directed to the home page after successfully logging in. | Logging in with a valid email and password was successful. However, the integration of Google Login is still in progress and has not been completed yet | FAILED |  |  | 2023-07-12 | The user should be directed to the home page after successfully logging in. | Logging in with a valid email and password was successful. However, the integration of Google Login is still in progress and has not been completed yet | PASSED |  |  | 07/19/2023 | The user should be directed to the home page after successfully logging in. | Logging in with a valid email and password was successful. However, the integration of Google Login is still in progress and has not been completed yet | PASSED |  |  |  | The user should be directed to the home page after successfully logging in. | [5 empty] | The user should be directed to the home page after successfully logging in.
Log-in with Google
| Invalid Log-in | TC-008 | Enter an invalid email | Verify that appropriate error messages are displayed for invalid login attempts. |  |  | Consistently displays the error message for invalid credentials. |  |  |  |  | 2023-06-13 | Consistently displays the error message for invalid credentials. | The app displayed technical error message which may confuse users. | FAILED | The app should display appropriate error messages to notify the user about the issues. For example: If the entered email is invalid: "Invalid email. Please enter a valid email address." If the entered password is incorrect: "Incorrect password. Please enter the correct password." |  | 2023-06-13 | Consistently displays the error message for invalid credentials. | The app displayed technical error message which may confuse users. | FAILED | The app should display appropriate error messages to notify the user about the issues. For example: If the entered email is invalid: "Invalid email. Please enter a valid email address." If the entered password is incorrect: "Incorrect password. Please enter the correct password." |  | 2023-06-13 | Consistently displays the error message for invalid credentials. | The app displayed technical error message which may confuse users. | FAILED | The app should display a more appropriate error messages to notify the user about the issues. For example: If the entered email is invalid: "Invalid email. Please enter a valid email address." If the entered password is incorrect: "Incorrect password. Please enter the correct password." |  | 2023-06-24 | Consistently displays the error message for invalid credentials. | The app displays the alert message "Incorrect password. Please enter the correct password" even though the email is the incorrect one. | FAILED | The app should display "Incorrect email. Please enter the correct email" instead. |  | 2023-07-12 | Consistently displays the error message for invalid credentials. | The app displays the alert message "Incorrect password. Please enter the correct password" even though the email is the incorrect one. | PASSED |  |  | 07/19/2023 | Consistently displays the error message for invalid credentials. | The app displays the alert message "Incorrect password. Please enter the correct password" even though the email is the incorrect one. | PASSED |  |  |  | Consistently displays the error message for invalid credentials. | [5 empty] | Consistently displays the error message for invalid credentials.
|  |  | Enter an incorrect password | [28 empty] | The app displays an alert message "Incorrect password. Please enter the correct password" | PASSED |  |  |  |  | The app displays an alert message "Incorrect password. Please enter the correct password" | PASSED |  |  |  |  | The app displays an alert message "Incorrect password. Please enter the correct password" | PASSED
| Nonexisting Account Validation | TC-009 | Enter an email address that does not exist in the system | Verify that the app displays an error message indicating that the account does not exist. |  |  | Consistently displays the error message for nonexisiting accounts. |  |  |  |  | 2023-06-13 | Consistently displays the error message for nonexisiting accounts. | The app displayed technical error message which may confuse users. | FAILED | The app should display appropriate error message. For example: "Account not found. Please check the email entered or create a new account." |  | 2023-06-13 | Consistently displays the error message for nonexisiting accounts. | The app displayed technical error message which may confuse users. | FAILED | The app should display appropriate error message. For example: "Account not found. Please check the email entered or create a new account." |  | 2023-06-13 | Consistently displays the error message for nonexisiting accounts. | The app displayed technical error message which may confuse users. | FAILED | The app should display appropriate error message. For example: "Account not found. Please check the email entered or create a new account." |  | 2023-06-24 | Consistently displays the error message for nonexisiting accounts. | The app displays appropriate alert message "Account not found. Please check the email antered or create a new account. | PASSED |  |  | 2023-07-12 | Consistently displays the error message for nonexisiting accounts. | The app displays appropriate alert message "Account not found. Please check the email antered or create a new account. | PASSED |  |  | 07/19/2023 | Consistently displays the error message for nonexisiting accounts. | The app displays appropriate alert message "Account not found. Please check the email antered or create a new account. | PASSED |  |  |  | Consistently displays the error message for nonexisiting accounts. | [5 empty] | Consistently displays the error message for nonexisiting accounts.
Enter a valid or invalid password
Preface | Sequential navigation through preface pages and Get started button | TC-011 | Tap on the next button. | Verify that users can navigate through the preface pages in a sequential order by using next button and that "get started" button on the last preface page functions properly. |  |  | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | [5 empty] | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. |  |  |  |  | 2023-06-13 | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | Each preface page is displayed in the correct order, ensuring the sequential progression of content. The next button smoothly transitions to the next preface page. Clicking the "get started" button successfully directs the user to the configuration and personalization pages, indicating a smooth transition to the subsequent stages of the application flow. | PASSED |  |  | 2023-06-13 | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | Each preface page is displayed in the correct order, ensuring the sequential progression of content. The next button smoothly transitions to the next preface page. Clicking the "get started" button successfully directs the user to the configuration and personalization pages, indicating a smooth transition to the subsequent stages of the application flow. | PASSED |  |  | 2023-06-24 | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | Each preface page is displayed in the correct order, ensuring the sequential progression of content. The next button smoothly transitions to the next preface page. Clicking the "get started" button successfully directs the user to the configuration and personalization pages, indicating a smooth transition to the subsequent stages of the application flow. | PASSED |  |  | 2023-07-12 | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | Each preface page is displayed in the correct order, ensuring the sequential progression of content. The next button smoothly transitions to the next preface page. Clicking the "get started" button successfully directs the user to the configuration and personalization pages, indicating a smooth transition to the subsequent stages of the application flow. | PASSED |  |  | 07/19/2023 | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | Each preface page is displayed in the correct order, ensuring the sequential progression of content. The next button smoothly transitions to the next preface page. Clicking the "get started" button successfully directs the user to the configuration and personalization pages, indicating a smooth transition to the subsequent stages of the application flow. | PASSED |  |  |  | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages. | [5 empty] | Each preface page should be displayed in correct order and the next button should seamlessly transition to the next page without any errors. Lastly, clicking "get started" button should direct the user to the configuration and personalization pages.
Tap on the "Get started" buton.
| Backward navigation through preface pages | TC-012 | Tap on the back button to go back to the previous pages. | Verify that users can navigate backward through the preface pages. |  |  | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | [5 empty] | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. |  |  |  |  | 2023-06-13 | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | Each preface page is displayed in the correct order when navigating backward, ensuring the sequential progression of content is maintained. The back button seamlessly transitions to the previous preface page without encountering any errors, allowing users to navigate back through the preface pages as expected. | PASSED |  |  | 2023-06-13 | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | Each preface page is displayed in the correct order when navigating backward, ensuring the sequential progression of content is maintained. The back button seamlessly transitions to the previous preface page without encountering any errors, allowing users to navigate back through the preface pages as expected. | PASSED |  |  | 2023-06-24 | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | Each preface page is displayed in the correct order when navigating backward, ensuring the sequential progression of content is maintained. The back button seamlessly transitions to the previous preface page without encountering any errors, allowing users to navigate back through the preface pages as expected. | PASSED |  |  | 2023-07-12 | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | Each preface page is displayed in the correct order when navigating backward, ensuring the sequential progression of content is maintained. The back button seamlessly transitions to the previous preface page without encountering any errors, allowing users to navigate back through the preface pages as expected. | PASSED |  |  | 07/19/2023 | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | Each preface page is displayed in the correct order when navigating backward, ensuring the sequential progression of content is maintained. The back button seamlessly transitions to the previous preface page without encountering any errors, allowing users to navigate back through the preface pages as expected. | PASSED |  |  |  | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors. | [5 empty] | Each preface page should be displayed in correct order when navigating backward and the back button should seamlessly transition to the previous page without any errors.
| Skip preface pages | TC-013 | Tap on the "skip" button on the top-right corner of the screen. | Verify that the skip option works. |  |  | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | [5 empty] | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. |  |  |  |  | 2023-06-13 | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | Upon clicking "skip," the user is successfully redirected to the configuration and personalization pages, bypassing the remaining preface pages. | PASSED |  |  | 2023-06-13 | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | Upon clicking "skip," the user is successfully redirected to the configuration and personalization pages, bypassing the remaining preface pages. | PASSED |  |  | 2023-06-24 | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | Upon clicking "skip," the user is successfully redirected to the configuration and personalization pages, bypassing the remaining preface pages. | PASSED |  |  | 2023-07-12 | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | Upon clicking "skip," the user is successfully redirected to the configuration and personalization pages, bypassing the remaining preface pages. | PASSED |  |  | 07/19/2023 | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | Upon clicking "skip," the user is successfully redirected to the configuration and personalization pages, bypassing the remaining preface pages. | PASSED |  |  |  | Upon clicking "skip," the user should be redirected to the configuration and personalization pages. | [5 empty] | Upon clicking "skip," the user should be redirected to the configuration and personalization pages.
User Configuraration and Personalization | Valid User Selection | TC-014 | Select user sex | Verify that the app accepts the input values and updates the user's profile accordingly. |  |  | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | [5 empty] | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | [5 empty] | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. |  |  |  |  | 2023-06-13 | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | After selecting valid user input, the user is directed to the next configuration page. | PASSED |  |  | 2023-06-24 | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | After selecting valid user input, the user is directed to the next configuration page. | PASSED |  |  | 2023-07-12 | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | After selecting valid user input, the user is directed to the next configuration page. | PASSED |  |  | 07/19/2023 | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | After selecting valid user input, the user is directed to the next configuration page. | PASSED |  |  |  | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page. | [5 empty] | Upon selecting a valid input value, the user should be able to click the next button and be directed to the "creating plan" page.
Select user age
Select user weight
Select user height
Select activity level
| Invalid User Selection | TC-015 | Select nothing from the sex and activity level selections. | Verify that the "next" button should not function. |  |  | Would not proceed to the next configuration page. | [5 empty] | Would not proceed to the next configuration page. | [5 empty] | Would not proceed to the next configuration page. |  |  |  |  | 2023-06-13 | Would not proceed to the next configuration page. | The next button is not clickable. | PASSED |  |  | 2023-06-24 | Would not proceed to the next configuration page. | The next button is not clickable. | PASSED |  |  | 2023-07-12 | Would not proceed to the next configuration page. | The next button is not clickable. | PASSED |  |  | 07/19/2023 | Would not proceed to the next configuration page. | The next button is not clickable. | PASSED |  |  |  | Would not proceed to the next configuration page. | [5 empty] | Would not proceed to the next configuration page.
Homepage | Add water intake | TC-016 | Enter a valid quantity of water intake in mL. | Verify that the app successfully adds the water intake and updates the progress towards the daily target. |  |  | The user interface should reflect the updated water intake appropriately. | [5 empty] | The user interface should reflect the updated water intake appropriately. | [5 empty] | The user interface should reflect the updated water intake appropriately. | [5 empty] | The user interface should reflect the updated water intake appropriately. | [5 empty] | The user interface should reflect the updated water intake appropriately. | [5 empty] | The user interface should reflect the updated water intake appropriately. |  |  |  |  | 07/19/2023 | The user interface should reflect the updated water intake appropriately. | The app accepts the input value for the water intake and displays it on the progress bar and constantly updates it with every input. | PASSED |  |  |  | The user interface should reflect the updated water intake appropriately. | [5 empty] | The user interface should reflect the updated water intake appropriately.
| Invalid water intake | TC-017 | Enter an invalid quanitity (negative value, zero, or non-numeric input) | Verify that the app displays an appropriate error message indicating the invalid input. |  |  | An error message should be displayed, informing the user about the invalid input. | [5 empty] | An error message should be displayed, informing the user about the invalid input. | [5 empty] | An error message should be displayed, informing the user about the invalid input. | [5 empty] | An error message should be displayed, informing the user about the invalid input. | [5 empty] | An error message should be displayed, informing the user about the invalid input. | [5 empty] | An error message should be displayed, informing the user about the invalid input. |  |  |  |  | 07/19/2023 | An error message should be displayed, informing the user about the invalid input. | The "Please select an option" message keeps on displaying on the app. | PASSED |  |  |  | An error message should be displayed, informing the user about the invalid input. | [5 empty] | An error message should be displayed, informing the user about the invalid input.
| Exceeding daily water intake target | TC-018 | Enter a water intake value greater than the daily recommended target. | Verify that the app prevents adding water intake exceeding the daily target and displays an appropriate error message. |  |  | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | [5 empty] | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | [5 empty] | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | [5 empty] | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | [5 empty] | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | [5 empty] | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. |  |  |  |  | 07/19/2023 | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | The app accepts the excessive input value and displays a 100% on the progress bar and does not accept any more input after that and displays a "Target water already achieved" message. | PASSED |  |  |  | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit. | [5 empty] | The app should validate the water intake entry and reject any values exceed the daily recommended target. An error message should be displayed, informing the user that the entered value exceeds the allowed limit.
| Missing Water Intake Entry | TC-019 | Clicking "add" without input | Verify that the app displays an appropriate error message indicating the missing input |  |  | An error message should be displayed, informing the user that input is required. | [5 empty] | An error message should be displayed, informing the user that input is required. | [5 empty] | An error message should be displayed, informing the user that input is required. | [5 empty] | An error message should be displayed, informing the user that input is required. | [5 empty] | An error message should be displayed, informing the user that input is required. | [5 empty] | An error message should be displayed, informing the user that input is required. | [5 empty] | An error message should be displayed, informing the user that input is required. | A "Please select an option" message is displayed, requesting the user to select an amount of water intake on the displayed options. | PASSED |  |  |  | An error message should be displayed, informing the user that input is required. | [5 empty] | An error message should be displayed, informing the user that input is required.
| Navigation Bars | TC-020 | Tap on each navigation bar. | Verify that the app navigates to the corresponding page accurately. |  |  | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | [5 empty] | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | [5 empty] | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | [5 empty] | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | [5 empty] | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | [5 empty] | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | [5 empty] | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | The app takes the user to the intended page and displays the content of that page selected. | PASSED |  |  |  | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page. | [5 empty] | The app should correctly take the user to the intended page. The navigation bars should provide a clear indication of the current active page.
Community Ranking | View Community Ranking | TC-021 | Click family ranking | Verify that the user's ranking is visible and accurately displayed in friends and family ranking. Additionally, it ensures that the ranking order is based on the accomplishment of their recommended daily water intake. |  |  | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher. | [5 empty] | The friends and family ranking should be prominently displayed in the Community Ranking section. Also, the user's ranking should be clearly visible within the ranking list and the ranking order accurately reflects the accomplishment of the recommended daily water intake, with higher achievers ranked higher.
Click friends ranking
Family Tracking | Sending reminder to a family member | TC-022 | Click the the button to send a reminder to a family member. | Verify that the user can send a reminder to a family member. |  |  | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent. | [5 empty] | The user should send a reminder to a family member without any error and receive a confirmation that the reminder is already sent.
Access the receiver account and confirm if the reminder is visible.
| Add a family member. | TC-023 | Click on the add member to the list. | Verify that the user can add new family member to the family tracking list. |  |  | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list. | [5 empty] | The app should display a form for the user to input the information of new family member. The newly added member should be displayed in family tracking list.
Enter the required information.
Check if the account is already added to the family tracking list.
Profile | Display of Badges | TC-024 | Complete the streak to earn a badge. | Verify if the earned badges of the user display accordingly in real time. |  |  | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly. | [5 empty] | Display the earned badges of the user in real time accordingly.
| Profile Actions | TC-025 | Click the settings button. | Verify that all buttons consistently respond to user clicks and perform the intended actions, such as switching pages. |  |  | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | [5 empty] | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | [5 empty] | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | [5 empty] | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | [5 empty] | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | [5 empty] | Upon clicking the button or tabs, they should perform their function, which is to switch pages. |  |  |  |  | 07/19/2023 | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | After clicking the settings button, the app redirects the user to the settings page that allows them to either submit a feedback or read the privacy policy and about us. On the hydration tips tab, it allows the user to view the tips by swiping left or right to navigate through the page. | PASSED |  |  |  | Upon clicking the button or tabs, they should perform their function, which is to switch pages. | [5 empty] | Upon clicking the button or tabs, they should perform their function, which is to switch pages.
Click the my reminder tab.
Click the hydration tips tab.
| Edit User Configuration and Personalization with Valid Value | TC-026 | Replace the user input values with valid ones. | Verify that the app updates the user information, creates a new plan, and reflects the changes throughout the app. |  |  | Update the user information, create a new plan, and reflect the changes throughout the app. | [5 empty] | Update the user information, create a new plan, and reflect the changes throughout the app. | [5 empty] | Update the user information, create a new plan, and reflect the changes throughout the app. | [5 empty] | Update the user information, create a new plan, and reflect the changes throughout the app. | [5 empty] | Update the user information, create a new plan, and reflect the changes throughout the app. | [5 empty] | Update the user information, create a new plan, and reflect the changes throughout the app. |  |  |  |  | 07/19/2023 | Update the user information, create a new plan, and reflect the changes throughout the app. | The app updates the user information, and activity level, creating a new plan based on the changes made in the user personalization and configuration. | PASSED |  |  |  | Update the user information, create a new plan, and reflect the changes throughout the app. | [5 empty] | Update the user information, create a new plan, and reflect the changes throughout the app.
| Edit User Configuration and Personalization with Invalid Value | TC-027 | Replace the user input values with invalid ones. | Verify that the app will display an error message and therefore not create a new plan. |  |  | Consistently displays an error message for invalid input values. | [5 empty] | Consistently displays an error message for invalid input values. | [5 empty] | Consistently displays an error message for invalid input values. | [5 empty] | Consistently displays an error message for invalid input values. | [5 empty] | Consistently displays an error message for invalid input values. | [5 empty] | Consistently displays an error message for invalid input values. |  |  |  |  | 07/19/2023 | Consistently displays an error message for invalid input values. | The app does not allow the user to continue after invalid input or no input at all. | PASSED |  |  |  | Consistently displays an error message for invalid input values. | [5 empty] | Consistently displays an error message for invalid input values.
Settings | Change Language | TC-028 | Select a different language from the list and save the changes. | Verify that the app interface and content are displayed in the selected language. |  |  | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface. | [5 empty] | The app consistently applies the chosen language throughout the user interface.
| App Rating | TC-029 | Click the Rate us tab. | Verify that the app redirects the user to the playstore. |  |  | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore. | [5 empty] | The app redirects the user to the playstore.
|  |  | Enter the rating and/or app review. | Verify that the playstore displays the submitted rating and review accurately. |  |  | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately. | [5 empty] | The playstore displays the submitted rating and review accurately.
| Feedback | TC-030 | Click the Feedback tab. | Verify that the app will display the feedback submission form. |  |  | The feedback submission form displays. | [5 empty] | The feedback submission form displays. | [5 empty] | The feedback submission form displays. | [5 empty] | The feedback submission form displays. | [5 empty] | The feedback submission form displays. | [5 empty] | The feedback submission form displays. | [5 empty] | The feedback submission form displays. | [5 empty] | The feedback submission form displays. | [5 empty] | The feedback submission form displays.
|  |  | Enter feedback. | Verify that the app acknowledges the user's feedback and displays a confirmation message. |  |  | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database. | [5 empty] | The app receives the feedback and stores it in the database.
| Privacy Policy | TC-031 | Click the Privacy policy tab. | Verify that the app consistently provides access to the privacy policy. |  |  | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page. | [5 empty] | The app display the privacy policy page.
Splash Screen | Splash Screen | TC-032 | Opens the app | Verify that the app displays the logo and name and directs to the Sign In Page |  |  | Displays the app logo and app name and directs to the Sign In Page | [5 empty] | Displays the app logo and app name and directs to the Sign In Page | [5 empty] | Displays the app logo and app name and directs to the Sign In Page | [5 empty] | Displays the app logo and app name and directs to the Sign In Page |  |  |  |  | 2023-06-24 | Displays the app logo and app name and directs to the Sign In Page | The app displays the app logo and app name and directs the user to the Sign In Page. | PASSED |  |  | 2023-07-12 | Displays the app logo and app name and directs to the Sign In Page | The app displays the app logo and app name and directs the user to the Sign In Page. | PASSED |  |  |  | Displays the app logo and app name and directs to the Sign In Page | The app displays the app logo and app name and directs the user to the Sign In Page. | PASSED |  |  |  | Displays the app logo and app name and directs to the Sign In Page | [5 empty] | Displays the app logo and app name and directs to the Sign In Page
Creating a Plan | Creating a Plan | TC-033 | Finish answering the user configuration page | Verify that the app will display the loading animation and direct the user to the Home Page |  |  | Displays the progress animation and directs the user to the Home page | [5 empty] | Displays the progress animation and directs the user to the Home page | [5 empty] | Displays the progress animation and directs the user to the Home page | [5 empty] | Displays the progress animation and directs the user to the Home page |  |  |  |  | 2023-06-24 | Displays the progress animation and directs the user to the Home page | The app displays the creating plan animation after finishing the configuration page and also directs the user to the home page. | PASSED |  |  | 2023-07-12 | Displays the progress animation and directs the user to the Home page | The app displays the creating plan animation after finishing the configuration page and also directs the user to the home page. | PASSED |  |  |  | Displays the progress animation and directs the user to the Home page | The app displays the creating plan animation after finishing the configuration page and also directs the user to the home page. | PASSED |  |  |  | Displays the progress animation and directs the user to the Home page | [5 empty] | Displays the progress animation and directs the user to the Home page
Hydration Pages | Sequential navigation through Hydration Tips pages | TC-034 | Swipes the screen to the right or left | Verify that users can navigate through the hydration tips pages in a sequential order by swiping left and right. |  |  | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | [5 empty] | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | [5 empty] | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | [5 empty] | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | [5 empty] | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. |  |  |  |  | 2023-07-12 | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | The hydration tips pages appear in the correct sequence and have smooth and responsive navigation between the pages when swiping, without any delays. | PASSED |  |  |  | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | The hydration tips pages appear in the correct sequence and have smooth and responsive navigation between the pages when swiping, without any delays. | PASSED |  |  |  | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay. | [5 empty] | Each hydration tips page should be displayed in correct order and the navigation of pages by swiping should not have any delay.
Weather Page | Updated display of data weather | TC-035 | User swipes down the page. | Verify that the refresh function works. |  |  | By swiping down the page, the latest weather data will be fetched and displayed. | [5 empty] | By swiping down the page, the latest weather data will be fetched and displayed. | [5 empty] | By swiping down the page, the latest weather data will be fetched and displayed. | [5 empty] | By swiping down the page, the latest weather data will be fetched and displayed. | [5 empty] | By swiping down the page, the latest weather data will be fetched and displayed. | [5 empty] | By swiping down the page, the latest weather data will be fetched and displayed. |  |  |  |  | 07/19/2023 | By swiping down the page, the latest weather data will be fetched and displayed. | The weather page refreshes after swiping down the page and updates to the latest weather data that changes real-time after an hour. | PASSED |  |  |  | By swiping down the page, the latest weather data will be fetched and displayed. | [5 empty] | By swiping down the page, the latest weather data will be fetched and displayed.